## Slide 1: Roadmap & Timeline
Launch Ready Planning (LRP)
ESTIMATED TIMELINE
Platform Planning
Portfolio Planning
Sprint 0
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Sprint 6
Sprint 7
Sprint 8
Sprint 9-n
Portfolio Accelerator
People Planning
Platform Party Promote 1st app to Dev
Security Jam & Operations Game Day
Platform Party Remediation
Move Party 1st App in Prod
Mobilize
Weekly Customer Executive Meeting
Pilot Application Discovery & Design
Wave Plan Baselined
Platform Buildout or Platform Validation Includes Landing Zone, Security, and Operations
Procure Tools & Deploy Delivery Kits
Load Tailored Backlogs
Sprint Ceremonies Begin
Weekly Sprint Cadence (Stand-ups, Demo, Retro, Planning)
Discovery Party
(Application scope, tooling)
Migration Planning
Validate Pilot Applications Discovery & Design
Migration Factory Deployment
Migration Accelerator
Pilot Applications Design Baselined
Migration Preparation Work
Platform Baselined
Migration Prep
Move Party n App in Prod
Migration Prep
Platform Accelerator
Platform Optimization Activities
People Accelerator
Mobilize Accelerator
Analysis Party
(output analysis)
Wave Plan Draft
Pilot Application Discovery & Design (continued)
App/Infra 7R Disposition, Categorization and Prioritization
Continuous Data Enrichment and Validation
Move Party n App in Prod
Migration Factory Testing
Migration Patterns Analysis
Leadership Alignment & Stakeholder Assessment
People Party
Case for Change
Org Change Readiness
OCM RACI & Risk Mitigation Strategy
Key Messaging for Communications
Change Strategy & Plan
Change Impacts
OCM Metrics
Notes: Mobilize provides customers flexibility and we work with customers to tailor the engagement based on the customer's desired business outcomes. The timeline below serves as a template or starting point that should be modified and tailored based on customer requirements.