## Application Assessment Party
Application Assessment Party
| Start Time | Duration Minutes | Topic | Application Owners | Application Developers | Cloud Programme Owner | Enterprise Architect(s) | Application Architect(s) | Cloud Platform Lead | Cloud Platfrom SMEs | On-prem platform SMEs | On-prem Networks SMEs | InfoSec | Third-Parties
Day 1 | 9:00 | 45 | Goal setting and business outcomes Objective: Document high-level Business drivers and customer outcomes (e.g., cost reduction, transformation, etc.) | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 9:45 | 60 | Application Prioritization Criteria (Optional) Objectives: 1/Review or Create the application prioritization criteria used to select applications. 2/Confirm sub-set of applications for deep dive | Req. | Opt. | Req. | Req. | Req. | Req. | Opt. | Opt. | Opt. | Req. | as needed
| 10:45 | 90 | Application Deep Dive Objective: 1/General App context. 2/App to infra mapping. 3/Security, Compliance, Regulatory requirements. 4/Service management overview. | Req. | Opt. | Opt. | Req. | Req. | Opt. | Opt. | Req. | Req. | Req. | as needed
| 12:15 | 45 | Launch Break
| 13:00 | 120 | AWS Application Architecture Design Objective: 1/ Target design options. 2/Operational considerations. 3/Estimated AWS run-cost and rightsizing. 4/Validated business outcomes | Req. | Opt. | Opt. | Req. | Req. | Req. | Req. | Opt. | Opt. | Req. | as needed
| 15:00 | 15 | Break
| 15:15 | 90 | Migration Strategy/Patterns Objective: 1/Outline Migration Strategy. 2/Cut-over considerations. 3/Migration tooling. 4/Decommission requirements | Req. | Opt. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 16:45 | 30 | Wrap-up Objectives: Review outcomes of the day and next steps | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
Day 2
Repeat day 1 agenda as needed depending scope
Day 3
Repeat day 1 agenda as needed depending scope