## Portfolio Discovery Party
Portfolio Discovery Party
| Start Time | Duration Minutes | Topic | Application Owners | Application Developers | Cloud Programme Owner | Enterprise Architect(s) | Application Architect(s) | Cloud Platform Lead | Cloud Platfrom SMEs | On-prem platform SMEs | On-prem Networks SMEs | InfoSec | Third-Parties
Day 1 | 9:00 | 30 | Opening / Goal Setting / Discovery Process Objectives: 1/Alignment. 2/Level-up on Discovery method. 3/Goals for the day. | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 9:30 | 60 | Business Drivers (Voice of the customer) and Guiding Principles Objectives: Document high-level Business drivers for customer outcomes (e.g., cost reduction, transformation, etc.) | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 10:30 | 60 | Application/Infrastructure Attributes and Data Requirements Objectives: 1/Socialize, discuss, and establish the key application and infrastructure attributes to be used for Portfolio Analysis. 2/Establish data repository | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 11:30 | 60 | Addressable Application and Infrastructure Scope - Part 1 Objectives: 1/ Walk-through, at a high-level, the applicaitons that the customer is considering for migration-. 2/Decide in-scope / out-of-scope as a target for discovery tooling | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 12:30 | 45 | Launch Break
| 13:15 | 60 | Addressable Application and Infrastructure Scope - Part 2 Objectives: 1/ Walk-through, at a high-level, the applicaitons that the customer is considering for migration-. 2/Decide in-scope / out-of-scope as a target for discovery tooling | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 14:15 | 75 | Application Prioritization Criteria Objectives: Establish default criteria for Wave 1 (or pilot apps) selection | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Opt. | Req. | as needed
| 15:30 | 30 | Wrap-up Objectives: Review outcomes of the day and next steps | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Opt. | Req. | as needed
Day 2 | 9:00 | 30 | Opening / Goal Setting Objectives: Goals for the day |  |  | Req. |  |  | Opt. | Opt. | Req. | Req. | Req. | as needed
| 9:30 | 150 | Discovery Tool Data Collection Roll-out Plan Objectives: A roll-out plan for starting data collection on targeted systems, including agent roll-out when required |  |  | Opt. |  |  | Opt. | Opt. | Req. | Req. | Req. | as needed
| 12:00 | 45 | Launch Break
| 12:45 | 120 | Discovery Tool Testing, Installation, Configuration and Start of Data Collection - part 1 Objectives: 1/ Tool installed, configured. 2/ Troubleshooting. 3/Start data collection |  |  | Opt. |  |  | Opt. | Opt. | Req. | Req. | Req. | as needed
| 14:45 | 15 | Break
| 15:00 | 90 | Discovery Tool Testing, Installation, Configuration and Start of Data Collection - part 2 Objectives: Start data collection |  |  | Opt. |  |  | Opt. | Opt. | Req. | Req. | Req. | as needed
| 16:30 | 30 | Wrap-up Objectives: Review of Party outcomes and next steps (e.g., adhoc sessions to iterate/finalize elements of the agenda) |  |  | Req. |  |  | Opt. | Opt. | Req. | Req. | Req. | as needed