## Portfolio Analysis Party
Portfolio Analysis Party
| Start Time | Duration Minutes | Topic | Application Owners | Application Developers | Cloud Programme Owner | Enterprise Architect(s) | Application Architect(s) | Cloud Platform Lead | Cloud Platfrom SMEs | On-prem platform SMEs | On-prem Networks SMEs | InfoSec | Third-Parties
Day 1 | 9:00 | 30 | Opening / Goal Setting Objectives: 1/Alignment. 2/Goals for the day. | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 9:30 | 60 | Asset & Dependency Discovery Output Review Objectives: High-level review of the data collected by the discovery tool | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 10:30 | 90 | Review/Validate Application Stacks - part 1 Important Note: Whenever possible, ensure any automated process to generate application stacks in the Discovery Tool are performed in advance. This is in order to avoid waiting times during the Party. Objectives: 1/Review/Validate application stacks identified by discovery tooling. 2/ Validate applications to infrastructure mapping. 3/ Identify high-level appliacation security requirements, service management attributes, business function. 4/Document application attributes. 5/ Identify Complex Applications (i.e., Big Rocks) | Req. | Opt. | Opt. | Req. | Req. | Opt. | Opt. | Req. | Req. | Req. | as needed
| 12:00 | 45 | Launch Break
| 12:45 | 120 | Review/Validate Application Stacks - part 2 Objectives: 1/Review/Validate application stacks identified by discovery tooling. 2/ Validate applications to infrastructure mapping. 3/ Identify high-level appliacation security requirements, service management attributes, business function. 4/Document application attributes. 5/ Identify Complex Applications (i.e., Big Rocks) | Req. | Opt. | Opt. | Req. | Req. | Opt. | Opt. | Req. | Req. | Req. | as needed
| 14:45 | 15 | Break
| 15:00 | 90 | Review/Validate Application Stacks - part 3 Objectives: 1/Review/Validate application stacks identified by discovery tooling. 2/ Validate applications to infrastructure mapping. 3/ Identify high-level appliacation security requirements, service management attributes, business function. 4/Document application attributes. 5/ Identify Complex Applications (i.e., Big Rocks) | Req. | Opt. | Opt. | Req. | Req. | Opt. | Opt. | Req. | Req. | Req. | as needed
| 16:30 | 30 | Wrap-up Objectives: Review outcomes of the day and next steps (e.g., adhoc sessions to iterate/finalize elements of the agenda) | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
Day 2 | 9:00 | 30 | Opening / Goal Setting Objectives: Goals for the day. | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed
| 9:30 | 120 | 7R Disposition Tree Objectives: 1/ Review/update 7R definition and agree to a common definition language. 2/Update the 7R disposition Tree based on known customer business drivers, architecture and technology. Note: This is a first approach at updating the tree, it will require subsequent iterations as more data becomes available. | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Opt. | Req. | as needed
| 11:30 | 60 | Iterate Application Prioritization Criteria Objectives: 1/ Upload Application Data to MPA and Establish a weight to key attributes to determine application prioritization (i.e., the order in which applications will be migrated) based on customer outcomes. 2/ Validate Wave 1 (or pilot apps) candidates | Req. | Opt. | Req. | Req. | Req. | Req. | Opt. | Opt. | Opt. | Req. | as needed
| 12:30 | 45 | Launch Break
| 13:15 | 60 | Validate Wave 1 (or pilot apps) candidates Objectives: Confirm candidates for Wave 1 based on appliation prioritization criteria | Req. | Opt. | Req. | Req. | Req. | Req. | Opt. | Opt. | Opt. | Req. | as needed
| 14:15 | 60 | Initial Wave Planning - Part 1 Objectives: Outline a first draft of a Wave Plan using MPA, at a high-level, considering key dependencies, dates and outcomes. This will be the base to keep iterating a Wave Plan. | Opt. | Opt. | Req. | Req. | Opt. | Req. | Opt. | Opt. | Opt. | Opt. | as needed
| 15:15 | 15 | Break
| 15:30 | 60 | Initial Wave Planning - Part 2 Objectives: Outline a first draft of a Wave Plan using MPA, at a high-level, considering key dependencies, dates and outcomes. This will be the base to keep iterating a Wave Plan. | Opt. | Opt. | Req. | Req. | Opt. | Req. | Opt. | Opt. | Opt. | Opt. | as needed
| 16:30 | 30 | Wrap-up Objectives: Review of Party outcomes and next steps | Req. | Opt. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | Req. | as needed