## Dashboard
AWS Database Migration Factory Dashboard
General Information | [6 empty] | Discovery | [9 empty] | Development |  |  |  |  | UAT | Prod
Wave | Database Names | Description | Customer Resources | AWS Resources |  | Key Issues | Questionnaire | Deep-Dive Session | Identify Apps and Dependencies | Identify Target Platform | DB LOE* | App LOE* | Assign Resources | Technical Access |  |  | Ready to Start Migration | DB Objects Converted | Data Migrated | App Code & Scripts Coverted | Handover/ Deployed to Dev | Customer Tested in Dev/UAT/Stage | Released to Prod
[5 empty] | RAG | [8 empty] | SRC DB | SRC Code | AWS/DMS
1 | Customer_DB1 |  | bob | john | G |  | Complete | Complete (8/6/20) | Customer_DB1 App | Aurora PostgreSQL | Small | Small | Complete | Complete | Complete | Complete | Started 8/18/20 | Completed (8/21/20) | Completed (8/24/20) | Completed (9/2/20) | Completed 9/3/20 (target 9/15/20) | Complete (9/25/20) | Complete (11/28/20)
1 | Customer_DB2 |  | mary | wolf | G |  | Complete | Complete (8/7/20) | Import/Export Jobs | Aurora PostgreSQL (serverless or RDS) | Small | Small | Complete | Complete | Complete | Complete | Started 8/18/20 | Completed (8/21/20) | Completed (8/24/20) | Completed (11/4/20) | Completed (11/4/20) | Complete | Complete (4/17/21)
1 | Customer_DB3 |  | jane | diana | G |  | Complete | Complete (8/12/20) | Client Facing Rest API, python scripts | Aurora PostgreSQL | Small | Small | Complete | Complete | Complete | Complete | Started 8/18/20 | Completed (8/21/20) | Completed (8/24/20) | Completed 9/10/20 (Target was 9/12/20) | Completed 9/10/20 (Target was 9/15/20) | Complete (11/6/20) | Complete (1/30/21)
1 | Customer_DB4 |  | joe | carlos | G |  | NA | NA | NA | Aurora PostgreSQL | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Complete (10/5/20) | Completed (10/5/20)
1 | Customer_DB5 |  | will | elise | G |  | Complete | Complete (8/28/20) | One Javascript App (node.js, typescript, knex) | Aurora PostgreSQL | Small | Small | Complete | Complete | Complete | Complete | Started 9/3/20 | Completed (9/10/20) | Completed (9/10/20) | Completed (9/16/20) | Completed 9/16/20 (target was 10/7/20) | Complete (11/6/20) | Complete (12/12/20)
2 | Customer_DB6 |  | jose | laurent | G |  | Complete | Complete (9/14/20) | DataLoad Jobs using Java/XML w/embedded SQL. AWS will convert SQL. Customer will update jobs. | Aurora PostgreSQL | NA | Small | Complete | NA | Complete | NA | Started 9/17/20 | NA | NA | Complete 10/23/20 | Complete 10/23/20 | Complete (5/26/21) | Complete (5/26/21)
2 | Customer_DB7 |  | tony | john | R | Go-live delayed due to competing priorities and budget constraints | Complete | Completed (9/17/20) | 4 C# Win Apps, Loader Jobs (Python) APIs (Python) | Aurora PostgreSQL | Large | Small | Complete | Complete | Complete | Complete | Started 9/23/20 | Completed 10/8/20 (Target was 10/30/20) | Completed 10/8/20 (Target was 10/30/20) | Completed (11/12/20) | Completed (11/12/20) | In Progress | Target Aug/Sep 2021
2 | Customer_DB8 |  | felix | wolf | G |  | Complete | Completed (9/28/20) | 2 C# API (Customer Facing and Interal), cleanup job (c#) | Aurora PostgreSQL | Small | Small | Complete | Complete | Complete | Complete | Started 9/29/20 | Completed (10/1/20) | Completed (10/1/20) | NA | Completed (10/1/20) | Completed (3/19/21) | Completed (3/20/21)
2 | Customer_DB9 |  | bob | diana | G |  | Complete | Completed (10/1/20) | Accessed only from DLL which already supports PostgreSQL | Aurora PostgreSQL | Small | NA | Complete | Complete | Complete | Complete | Started 10/1/20 | Completed 10/5/20 | Completed 10/5/20 | Completed (10/8/20) | Completed (10/22/20) | Completed (1/12/21) | Completed (1/14/21)
2 | Customer_DB10 |  | mary | carlos | G |  | Complete | Completed (10/1/20) | Accessed only from DLL which already supports PostgreSQL | Aurora PostgreSQL | Small | NA | Complete | Complete | Complete | Complete | Started 10/1/20 | Completed 10/5/20 | Completed 10/5/20 | Completed (10/9/20) | Completed (10/28/20) | Completed (1/12/21) | Completed (1/14/21)
2 | Customer_DB11 |  | jane | elise | R | Testing was delayed due to competing priorities. | Complete | Completed (9/11/20) | .Net Web API, Perl Scripts to bulk upload/extract | Aurora PostgreSQL | Small | Small | Complete | Complete | Complete | Complete | Started 9/17/20 | Completed (9/29/20) | Completed (10/5/20) | Completed (10/30/20) | Completed (12/21/20) | In progress | Target 7/10/21
3 | Customer_DB12 |  | joe | laurent | Y | Go-live was delayed due to competing priorities and budget constraints | Complete | Completed (10/9/20) | 2 Windows Apps accessing db and 1 Python Job extracts data | Aurora PostgreSQL | Small | Medium | Complete | Complete | Complete | Complete | Started 10/15/20 | Completed 10/23/20 | Completed 10/23/20 | Completed (2/26/21) | Completed (3/5/21) | In Progress | Target July 2021
3 | Customer_DB13 |  | will | john | G |  | Complete | Completed (10/14/20) | 1 C# Winforms App, 1 C# API, 1 C# Feed Job | Aurora PostgreSQL | Small | Small | Complete | Complete | Complete | Complete | Started 10/16/20 | Completed 10/29/20 | Completed 10/29/20 | Completed (12/11/20) | Completed (12/14/20) | Completed (4/9/21) | Completed (4/10/21)
3 | Customer_DB14 |  | jose | wolf | G |  | Complete | Completed (10/15/20) | 1 C# Winforms App, 1 Python API | Aurora PostgreSQL | Small | Medium | Complete | Complete | Complete | Complete | Started 10/27/20 | Completed 11/3/20 | Completed 11/3/20 | Completed (12/31/20) | Completed (12/31/20) | Completed 2/12/21 | Completed (2/13/21)
3 | Customer_DB15 |  | tony | diana | G |  | Complete | Completed (10/15/20) | 1 C# Winforms App, 1 Python API, 3 Python export jobs | Aurora PostgreSQL | Small | Large | Complete | Complete | Complete | Complete | Started 10/29/20 | Completed 11/18/20 | Completed 11/18/20 | Completed (2/12/21) | Completed (2/18/21) | Completed (4/23/21) | Completed (4/24/21)
3 | Customer_DB16 |  | felix | carlos | NA | Customer decided to target another platform for migration. | NA | Completed (10/21/20) | NA | Neptune | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | Customer_DB17 |  | bob | elise | Y | Customer is now testing RDS in dev env. | NA | Completed (10/20/20) | NA | RDS | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Target June 2021 (RDS)
3 | Customer_DB18 |  | mary | laurent | G |  | Complete | Completed (10/27/20) | 1 C# Webforms, 30-40 Perl Scripts | Phase 1 (RDS or EC2); Phase 2 PostgreSQL (Aurora or Redshift) | X-Large | Medium | Complete | Complete | Complete | Complete | Started 11/9/20 | Completed (2/16/21) | Completed (2/16/21) | Completed (2/16/21) | Completed (2/16/21) | Target Mar-Jun 2021 | Target Aug 2021
4 | Customer_DB19 |  | jane | john | G |  | Complete | Completed (9/9/20) | Web JS/C# Apps E2I - email interface Rest APIs | Aurora PostgreSQL & S3/Elastisearch | XXX-L | XL | Complete | Complete | Complete | Complete | Started 10/5/20 | Completed 12/22/20 | Completed (4/19/21) | Completed (4/19/21) | Completed (5/4/21) | Target July 2021 | Target Aug 2021
4 | Customer_DB20 |  | joe | wolf | G |  | Complete | Complete (8/10/20) | App calls DB thru DLL | Aurora PostgreSQL | Large | XXX-Large | Complete | Complete | Complete | Complete | Started 1/6/21 | Completed (2/26/21) | Completed (3/31/21) | Completed (5/27/21) | Completed (5/27/21) | Target to Begin Mid July | TBD
4 | Customer_DB21 |  | will | diana | G |  | NA | Completed (11/9/20) | Angular GUI and jobs all access through c# API | DynamoDB | Medium | Medium | Complete | Complete | Complete | Complete | Started 11/18/20 | Completed (1/15/21) | Completed (1/15/21) | Competed (3/22/21) | Completed (3/22/21) | To Start 6/1/21 | Target June 2021
4 | Customer_DB22 |  | jose | carlos | G |  | Complete | Completed (11/17/20) | Web GUI (C#) to write messages and a C# API for reads. | Aurora/RDS PostgreSQL | Small | Small | Complete | Complete | Complete | NA | Started 12/2/20 | Completed (12/16/20) | Completed (12/16/20) | NA | Completed (12/16/20) | Completed (6/21/21) | Completed (6/21/21)
4 | Customer_DB23 |  | tony | elise | G |  | Complete | Completed (11/13/20) | Angular GUI, perl/c++/c# jobs, but all db access through perl cgi layer or perl modules | Aurora PostgreSQL | Medium | NA | Complete | Complete | Complete | Complete | Started 12/14/20 | Completed (2/26/21) | Completed (2/26/21) | NA | Completed (3/9/21) | In Progress | TBD
4 | Customer_DB24 |  | felix | laurent | G |  | Complete | Completed (12/3/20) | 6 Perl Jobs Call .SQL files, a new C# App | Aurora PostgreSQL | Medium | Medium | Complete | Complete | Complete | Complete | Started 12/14/20 | Completed (2/8/21) | Completed (2/8/21) | Completed (2/8/21) | Completed (4/29/21) | In Progress | TBD
5 | Customer_DB25 |  | bob | john | G |  | Complete | Completed (1/19/21) | Other Apps and Anular GUI access DB through C# WebAPI only | Aurora PostgreSQL | Small | Small | Complete | Complete | Complete | Complete | Started 2/8/21 | To Re-Start 5/7/21, Target Completion 6/21/21 | To Re-Start 5/7/21, Target Completion 6/21/21 | To Re-Start 5/7/21, Target Completion 6/21/21 | Target 6/25/21 | TBD | TBD
5 | Customer_DB26 |  | mary | wolf | G |  | Complete | Completed (1/11/21) | C# .Net App, ASP/ASP.Net App, Export Jobs (C#/Python), C++ API | Aurora PostgreSQL | XXX-Large: DB = 28m | XXX-Large: .Net = 14m | Complete | Complete | Complete | Complete | Started 2/18/21 | Target 11/22/21 | Target 11/22/21 | Target 11/22/21 | Target Jan 2022
5 | Customer_DB27 |  | jane | diana | G |  | Complete | Completed (1/21/21) | Perl Jobs to manage pipeline, C#.Net App for QA testing, Python Data Feeds, New QA App in Python & Vue.js | Aurora PostgreSQL | X-Large: DB = 13w | XXX-Large: .Net = 4w Python = 24w | Complete | Complete | Complete | Complete | Started 2/15/21 | Completed (5/14/21) | Completed (5/14/21) | Completed (6/9/21) | Target 6/18/21
5 | Customer_DB28 |  | joe | carlos | R | Latency Sensitive, may need to migrate upstream on-prem components along with DB. Stakeholder has not decided whether to proceed. | Complete | Completed (1/13/21) | Consumers access through C# API, Import Jobs are SSIS Pkg | Aurora PostgreSQL | XXX-Large: DB = 16w SSIS = 15w Wombat SQL = 10w | Medium: .Net = 4w Python = 3w | TBD | Complete | Complete | IP | TBD | TBD | TBD | TBD | TBD
5 | Customer_DB29 |  | will | elise | R | Customer decides cost/benefit is not justified. | Complete | Completed (1/22/21) | 3 C# Apps to maintain security data, Python Data Feeds, Python API for consumers | Aurora PostgreSQL | Small: DB = 1w | Large: .Net = 8w Python 14w | TBD | Complete | Complete | NA | Started 3/1/21 | Completed (3/5/21) | TBD | TBD | TBD
5 | Customer_DB30 |  | jose | laurent | Y | Delayed due to Customer resource conflicts | Complete | Completed (3/10/21) | Web UI, Support UI, and Downstream systems all access DB thru .Net API. | Aurora PostgreSQL | Medium: DB = 8w | NA | Complete | Complete | Complete | Complete | Started 3/24/21 | Completed (5/24/21) | Completed (5/24/21) | NA | Completed (6/4/21) | Customer Team to convert App in June, Testing to start July | TBD
5 | Customer_DB31 |  | tony | john | G |  | Complete | Completed (3/11/21) | C# App, Python Jobs | Aurora PostgreSQL | Medium: DB = 7w | Large: .Net = 9w Python 1w | Complete | Complete | Complete | Complete | Started 3/24/21 | Completed (5/24/21) | Completed (5/24/21) | Completed (5/24/21) | Completed (6/4/21) | In Progress | Target July
5 | Customer_DB32 |  | felix | wolf | G |  | Complete | Completed (3/16/21) |  | Aurora PostgreSQL & Babelfish | Small | Small | Complete | Complete | Complete | Complete | Started 3/16/21 | TBD | TBD | TBD | TBD
6 | Customer_DB33 |  | bob | diana | Y | Testing is delayed | Complete | Completed (4/12/21) | No app code. | Aurora PostgreSQL | Small: DB = 3w | NA | Complete | Complete | Complete | Complete | Started 4/20/21 | Completed 4/20 | Completed 4/20 | NA | Target June 2021
6 | Customer_DB34 |  | mary | carlos | G |  | Complete | Completed (4/15/21) | ASP.Net App | Aurora PostgreSQL | Small: DB = 2w | Small: App = 4w | Complete | Complete | Complete | Complete | Started 4/20/21 | Completed (5/5/21) | Completed (5/5/21) | Completed (5/28/21) | Target 6/11/21
6 | Customer_DB35 |  | jane | elise | G |  | Complete | Completed (4/29/21) | ASP.Net, C# APIs | Aurora PostgreSQL | XXXL: DB = 20m | XXL: App = 16w | Complete | Complete | Complete | Complete | TBD | TBD | TBD | TBD | TBD
6 | Customer_DB36 |  | joe | laurent | G |  | Complete | Completed 5/7/21 | Java API's call StoredProcs, ETL tool | Aurora PostgreSQL | XX Large: DB = 16w | TBD (should be minimal) | Complete | Complete | Complete | Complete | Started 5/31/21 | Target 8/13/21 | Target 8/13/21 | TBD (Customer to do this) | Target 8/20/21
6 | Customer_DB37 |  | will | john | G |  | Complete | Completed (5/14/21) | Angular FE access db through c# APIs. Analytics APIs have limited python | Aurora PostgreSQL | Small: DB = 1w | Small: App = 2w | Complete | Complete | NA | Complete | Started 5/31/21 | Completed (6/7/21) | Completed (6/7/21) | Completed (6/25/21) | Completed (6/25/21)
6 | Customer_DB38 |  | jose | wolf |  |  | Complete | Completed (5/17/21) | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | Customer_DB39 |  | tony | diana | G |  | Complete | Completed (6/8/21) | All db access is through Java API | TBD | TBD | TBD | TBD | Complete | Complete | IP | TBD | TBD | TBD | TBD | TBD
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Level of Effort to Migrate Schema, App Code, Unit Test and Be Ready for Factset team to start their testing. See Tab below for definitons
Note on M4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Level of Effort to Migrate Schema, App Code, Unit Test and Be Ready for Factset team to start their testing. See Tab below for definitons

## LOE Defn
Level of Effort Definition
The number of man hours to convert database schema, application code, unit test and deploy to dev environment for Customer team to begin their testing
Category | LOE
Small | 2-4 weeks
Medium | 5-8 weeks
Large | 9-12 weeks
X-Large | 13-15 weeks
XX-Large | 16-18 weeks
XXX-Large | 18+ weeks