## Program Plan
Project Schedule/Deliverables
[13 empty] | Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9 |  | Sprint 10 |  | Sprint 11 |  | Sprint 12 |  | Sprint 13 |  | Sprint 14 |  | Sprint 15 |  | Sprint 16 |  | Sprint 17 |  | Sprint 18 |  | Sprint 19 |  | Sprint 20 |  | Sprint 21
 | time axis 2021-02-01 to 2021-12-06
S.No | EPIC | Detailed Task | Duration | Start Date | Finish Date | Owner | Dependencies | Current Status | % Complete | Deliverables/Outcomes | Comments
1 | Project Initiation | Resource Onboarding and Access | 3 wks |  |  | AWS |  | In Progress | bar: 2021-02-08 to 2021-02-22
|  | XXX PoC | 4 wks | 2021-02-01 | 2021-02-26 | AWS, Customer |  | In Progress | bar: 2021-02-01 to 2021-02-22
|  | EDF Overview | 1 hr | 2021-02-02 | 2021-02-02 | AWS |  | Completed | bar: 2021-02-01
|  | Scope Alignment | 1 wk |  |  | AWS, Customer |  | In Progress | bar: 2021-02-08
|  | Project Outcomes, Planning, Prioritization, High Level Backlogs (LRP) | 1 wk |  |  | AWS |  | Not Started | bar: 2021-02-15 to 2021-02-22
Finalize Program Timelines | bar: 2021-02-15 to 2021-02-22
|  | Establish communications plan, RAID Logs, etc | 1 wk |  |  | AWS |  | Not Started | bar: 2021-02-22
|  | Setup Project Tools (Confluence, Jira, Google,etc) | 2 wk |  |  | AWS |  | Not Started | bar: 2021-02-15 to 2021-02-22
Finalize Program Backlog | bar: 2021-02-15 to 2021-02-22
|  | Define Project RACI | 3 wk |  |  | AWS |  | Not Started | bar: 2021-02-22
|  | Milestone : Project Kickoff | 4 wk |  |  | AWS |  | Not Started | bar: 2021-02-22
|  | Project Planning, Governance and Management | On-going |  |  | AWS |  | Not Started
2 | DataBase Migration Wave Plan | DB 1 | 3 wks |  |  | AWS |  | Not Started | bar: 2021-03-01 to 2021-07-19
|  | DB 2 | 3 wks |  |  | AWS |  | Not Started | bar: 2021-03-01 to 2021-06-07
|  | DB 3 | 18 wks |  |  | AWS |  | Not Started | bar: 2021-03-01 to 2021-11-22
8 | Training/Knowledge Transfer Sessions | Conduct Training | 1 wk |  |  | AWS |  | Not Started
|  | Conduct Deep Dive Sessions | 1 wk |  |  | AWS |  | Not Started
| Production Deployment | BRT (Business Readiness Testing) | 1 wk |  |  | Customer |  | Not Started
|  | Day 2 - Knowledge Transfer | 1 wk |  |  | AWS |  | Not Started
|  | Milestone: Go-live – assist Customer with full go-live support during migration. | 1 wk |  |  | AWS |  | Not Started
10 | Project Closure | Warranty | 1 wk |  |  | AWS |  | Not Started
|  | Lessons Learned | 1 wk |  |  | AWS |  | Not Started
|  | Survey | 1 wk |  |  | AWS |  | Not Started
|  | Project Closure | 1 wk |  |  | AWS |  | Not Started

## Project Teams
Migration Team (MT) | MT Lead | Team Member(s)
MT 1 | Lead1 | App Migration and DB Consultants
MT 2 | Lead2 | App Migration and DB Consultants
MT 3 | Lead3 | App Migration and DB Consultants
Support Team | Lead 4 | Java Developer, Security Consultant, DevOps

## Wave Plan
Wave Plan |  |  | WAVE 1 | [7 empty] | WAVE 2 | [7 empty] | WAVE 3 | [7 empty] | WAVE 4
DataBase Group | DataBase | Migration Team | 2021-03-01 | 2020-03-08 | 2019-03-16 | 2018-03-23 | 2017-03-30 | 2016-04-06 | 2015-04-14 | 2014-04-21 | 2013-04-28 | 2012-05-05 | 2011-05-13 | 2010-05-20 | 2009-05-27 | 2008-06-03 | 2007-06-11 | 2006-06-18 | 2005-06-25 | 2004-07-02 | 2003-07-10 | 2002-07-17 | 2001-07-24 | 2000-07-31 | 1999-08-08 | 1998-08-15 | 1997-08-22 | 1996-08-29 | 1995-09-06 | 1994-09-13 | 1993-09-20 | 1992-09-27 | 1991-10-05 | 1990-10-12 | 1989-10-19 | 1988-10-26 | 1987-11-03 | 1986-11-10 | 1985-11-17 | 1984-11-24
G1 | DB1 | MT 1 | Finalize Backlog and Sprint Plan Re-Assessment | Re -Assessment | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | Data Load | Functional Testing/ QA | UAT/Performmance Test | Cutover
G1 | DB2 | MT 2 | [19 empty] | Finalize Backlog and Sprint Plan Re-assessment | Re- -Assessment | DB Migration | DB Migration | SQL Coversion & DB Migration | SQL Coversion | SQL Coversion | SQL Coversion | SQL Coversion | SQL Coversion | SQL Coversion | SQL Coversion | Data Load | Functional Testing/ QA | UAT/Performmance Test | Cutover
G1 | DB3 | MT 2 | Finalize Backlog and Sprint Plan Re-assessment | SQL Coversion & DB Migration | Data Load | Functional Testing/ QA | UAT/Performmance Test | Cutover
G1 | DB4
G1 | DB5
G1 | DB6
G1 | DB7
G1 | DB8
G2 | DB9 | MT 2 | Finalize Backlog and Sprint Plan Re-assessment | Re- -Assessment | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | SQL Coversion & DB Migration | Data Load | Functional Testing/ QA | UAT/Performmance Test | Cutover
G3 | DB10
G3 | DB11
G3 | DB12
G3 | DB13 | MT 1 | [16 empty] | Finalize Backlog and Sprint Plan Re-assessment | TBD
G3 | DB14 | MT 2 | [6 empty] | Finalize Backlog and Sprint Plan Re-Assessment | DB Migration | SQL Query Conversion | SQL Query Conversion | SQL Query Conversion | SQL Query Conversion | SQL Query Conversion | SQL Query Conversion | SQL Query Conversion | SQL Query Conversion | SQL Query Conversion | Data Load | Functional Testing/ QA | UAT/Performmance Test | Cutover | Cutover |  |  | Finalize Backlog and Sprint Plan | Assessment | Assessment | Coversion & Migration | Coversion & Migration | Data Load | Functional Testing | Cutover
G3 | DB15 | MT 2 | Finalize Backlog and Sprint Plan Re-assessment | TBD | [28 empty] | Finalize Backlog and Sprint Plan | Assessment | Assessment | Coversion & Migration | Coversion & Migration | Data Load | Functional Testing | Cutover
[33 empty] | Finalize Backlog and Sprint Plan | Assessment | Assessment | Coversion & Migration | Coversion & Migration | Data Load | Functional Testing | Cutover

## Workstreams
S.No | Workstreams | Responsible
1 | Engagement Management/Governance
2 | Database Migration
3 | App Migration?
4 | Security?
5 | DevOps?
6 | App Migration?

## SOW Scope Clarifications
S.No | Clarifications | Decision
1 | Scope : Application code refactoring. PL SQL convesion in scope currently we are not integrating with the application
2 | Operating model ?
3 | Security consultant role
4 | Java consultant role? Assigned to DB migration role
5

## Engagement Management_Governanc
OUTCOMES | Sprint 4 (August 12 - August 25) |  | Sprint 5 (August 26 - September 8)
Example: Create a self-service portal for XXXXXX company | Story | Dependencies | Story | Dependencies
Establish Engagement governance model and on-going cadence | Establish communications plan - Include stakeholders from Account Team, ProServe, DLT, DoIT - Identify primary points of contact on each team - Internal meetings to ensure teams are aligned - External meetings to communicate the plan and get approval |  | Get consensus on escalation path & process
Establish change control process | JIRA Sprint Tracking - User story tracking - Acceptance tracking mechanism |  | Establish process for requirements sign-off - having well defined scope, requirements locked in before sprint starts | Requirements Certification. Need to happen before sprint(s) starts
Establish communications plan & escalation process | Establish process to marry the outcomes PR/FAQ of the Delivery Innovation team and the PR/FAQ of the LRP |  | Establish process for UAT sign-off - having a UAT sign off before we deploy functionality into PROD | PROD Go/No-Go Decision
Establish process for requirements gathering | Weekly Status Reports - Tasks completed in the prior week - Tasks planned for next week - Financial tracker - Budget status (spend to date by invoice period & calendar month) - Risk tracker (RAID log) |  | committing to two week sprints (Weds - Tu, vs Mon - Fri)
| Process for onboarding and offboarding |  | Partner - onboarding, status reporting, workstream scope/outcomes,
| Update Team Calendar |  | Requirements Product Manager on Dev team | Need to prioritize this
RISKS | Sprint 6 (September 9 - September 22) |  | Sprint 7 (September 23 - October 6)
Example: data cannot be exported from the AS400 | Story | Dependencies | Story | Dependencies
| Session with Senior Managers from Customer Team to help understand the business | Need to prioritize this user story
Create RACI matrix
| Confirm Workstream definition/ charter | Needs to be completed by 8/4
Create the roadmap (end-to-end plan with schedule and budget)
Establish change control process / Change request process
PARKING LOT | Sprint 8 (October 7 - October 20) |  | RISKS
| Story | Dependencies