## Checklist for a DB Migration
Database Migration Checklist for Migrating Databases
Stage | Task | Workshop/Meeting Involved | Artifact (Outcome) | Teams Involved | Template Reference (sample)
Pre Engagement | SoW Creation/Review |  | SoW | Customer, AWS
| DB Pre Assessment | Yes | DB Questionaire, Pre Assessment Analysis, Estimations, Discovery and Delivery Kit | Customer, AWS
| TCO |  |  | Customer, AWS
Engagement KickOff | Kick Off meeting | Team Introduction, Kick off PPT |  | Customer, AWS
|  | Planning, LRP Meetings |  | Customer, AWS
| Align on Toolings |  | Backlog, Content | Customer, AWS
| Stakeholder Identification |  | Escalation Matrix | Customer, AWS
| Create and review RACI |  | RACI | Customer, AWS
| Create a RAID Log |  | RAID Log | Customer, AWS
| Create a Decision Log |  | Decision Log | Customer, AWS
| SoW Review, Scope Alignment |  |  | Customer, AWS
| Delivery Mechanism - Agile/Waterfall | EDF walkthrough | EDF presentation | Customer, AWS
| SFDC Set Up, Resource Onboarding |  | Note: Use T&M Financial Tool for budget tracking and details | EM (AWS Internal)
| Slack/Chime Channel Set Up |  | Note: Slack Channel should be created Private | EM (AWS Internal)
| Email D List set up (Internal) |  | D List creation steps/screenshots/Kmine/wiki link | EM (AWS Internal)
| Email D List set up (External) |  |  | PM (Customer)
| Meeting Cadences |  |  | Customer, AWS
| Communication Channels |  |  | Customer, AWS
| Partner Integration to all above steps |  |  | EM(AWS)
| Weekly Status Report Overview |  | DB Weekly Status Report | EM(AWS) | https://collaborate-corp.amazon.com/nuxeo/ui/#!/doc/592159b5-d0bd-4be7-b588-107df742b1d0
| Steering Committee Review (Internal) |  |  | EM(AWS)
| Steering Committee Review (External) |  |  | Customer, AWS | https://collaborate-corp.amazon.com/nuxeo/ui/#!/browse/default-domain/sections/Templates/ProServe%20Templates/Database%20Migration%20Weekly%20Progress%20Report%20for%20Stakeholders%20(PPT)
| LRP | Program Planning Wave Planning LRP | Program Plan Documentation LRP Outcomes Backlog, Content Finalized RACI DB Scope Alignment Key Milestones Alignment
| Gather Immersion Day/Training & Enablement Requirements |  |  | Customer, AWS
| Consolidated Access/SW Requirements |  | Readiness Checklist | Customer, AWS
| Set up APM/Collboration tools and spaces like JIRA, Confluence, Sharepoint etc |  | Content, Backlog | EM(AWS)
Design/Architecture | DB Discovery Session (for each DB) | Discovery Meeting | DB Questionaire Scope Document | Customer, AWS
| Gather Additional Features Requirement, Security and Complaince Requirement |  | Scope Document | Customer, AWS
| Environment Setup |  |  | Customer, AWS
| Re-Assessment/Assessment Review DB and confirm scope of conversion, estimation (Tools like SCT/SSMA can be leveraged by the technical team) |  | Scope Document Estimations | AWS | https://collaborate-corp.amazon.com/nuxeo/ui/#!/browse/default-domain/workspaces/ProServe%20Goldemine%20Workspace/ProServe%20Goldmine%20Auto-Created.1589356312656
| Prepare and Review Estimations |  | Scope Document Estimations | Customer, AWS
| Clarify and Align on scope |  | Scope Document Estimations | Customer, AWS
| Gather Priority of Schema Conversion (if any) |  |  | Customer, AWS
| Low Level Delivery Schedule Plan |  |  | AWS | https://collaborate-corp.amazon.com/nuxeo/ui/#!/browse/default-domain/workspaces/ProServe%20Goldemine%20Workspace/DB%20Migration%20End-2-End%20Plan%20Template
Migration (Each DB, each schema) | Data Type Alignment |  |  | Customer, AWS
| Schema Conversion & Creation |  |  | AWS
| Data Migration - Data Load(Full) |  | CFTs | AWS
| Provide Application SQL for Conversion |  | Scripts | Customer
| Perform Application SQL conversion |  | Scripts | AWS
| PLSQL code conversion |  | Scripts | AWS
| Sanity Test |  |  | AWS
| Functional Test Creation |  | AWS will provide Functional TC sample format if required | Customer
| Functional Test - Run |  | Test Output | AWS
| Data Migration - Data Load(CDC) |  | CFTs | AWS
| Application SQL Integration |  | App SQLs | Customer
| Object Count Validation |  | Object Validation Document | AWS
| Run Security Tool on DMS CFTs (CFN-Nag) |  | Output of security Run | AWS(Internal)
| DB Security Review and Assessment |  | Security Matrix | AWS(Internal)
| Delivery Kit (DB, DMS) <if using DMS> |  | Delivery Kit | AWS
| Application Set up with Target DB |  | Test Tracker | Customer
| End to End Application Testing |  | Test Tracker | Customer, AWS
| Performance Testing |  | Test Tracker | Customer, AWS
| AWS Support |  | Test Tracker | Customer, AWS
| PoC Documentation |  | Delivery Kit + Any Specific Documentation for additional features delivered | AWS
| Sign off |  | JIRA/Email | Customer
Stage Environment Readiness | AWS Support |  |  | AWS
| Environment Readiness and DB Deployment |  |  | Customer
Cut-Over Planning | Cut-Over activities |  |  | Customer
| AWS Support |  |  | AWS
Go Live | Go Live Tasks |  |  | Customer
| AWS Support |  |  | AWS