## DB_Migration_Summary
Source Database Engine
Target Database Engine
Efforts of Estimate for Database Migration | DB Name | Database Object Details |  | Other Noteworthy Observations | Size/Value
| DB Name-1 |  | COUNT | Active Dataguard
AWS Infrastrucute Provisioning & Architecture Design Review |  | Object Type | DB Name-1 | RAC
Infra Setup & Provisioning Services used during Migration- APG,DMS,CFT,Terraform etc | 0 | Schemas |  | Partitioning, on Date/Yearly
Design Review - Database design, failover/HA | 0 | Table |  | RMAN
Schema & PL/PgSQL Code Conversion |  | Table Partition |  | ASM
Schema Conversion | 0 | Index |  | Flashback
PL/SQL Conversion | 0 | Constraints |  | Instance Level
Review the Data Types, Proc's/Func | 0 | Sequence |  | Max Log Switches
Sanity Testing - Without data | 0 | Trigger |  | REDO Per Day
Data Migration |  | Package |  | Object Level
DX- Oracle-DMS-APG | 0 | Package - Function |  | Top Schema Size- CP01
Sanity Testing |  | Package - Procedure |  | Top Table Size
Performance Testing - With data | 0 | Package - Type |  | Top LOB Table Size (Images and PDFs)
|  | Procedures |  | Table with Max Partitions
Embeded Application SQL's Migration |  | Function |  | Table with Max Columns
Application SQL's |  | Synonym |  | Table with Max num_rows
AWS Support for Non Prod Environment |  | DB Links |  | Security
Propogation of Schema, Code changes to higher environment(QA,SIT,Pre-Prod) | 0
Full Data + CDC + Creation of Secondary objects on Staging environemt | 0 | MV's |  | Data Encryption at Rest
Failover/HA testing with application testing* - Staging, Production(until cutover) | 0 | External Table |  | Compliance Requirements
Tuning , Regression & Load Testing Support Efforts - QA | 0 | Views |  | Column Level encryption
AWS Support for Prod Environment |  | Type |  | Password Profiles
During Production Cutover | 0 | Job |  | Database Logon Trigger
Post Production Support(Database Performance Issues) | 0 | LOB |  | Auditing Requirements
Efforts for Additional Features |  | Database Size
Advanced Security, Compression & Encryption | 0
Password Profiles & Database Authentication using IAM/AD | 0
Compliance - PCI DSS requirements 3.2.1, HIPPA, GDPR | 0
Auditing(Need to check for exact requirements) | 0
Monitoring using Performance Insights, CW, Database Notifications, Enhanced Monitoring | 0
Total Person Days [A] | 0
Training & Enablement Program by AWS to Customer_Name
Part-1 - Primer Topics- Aurora PostgreSQL, DMS, CW,SNS,CFT ( Before Project KickOff) | 0
Part-2 - Dive Deep Topics - Query Tuning, Database Tuning, PL/PgSQL Best Practises, Operational/Maintenance Activities on Aurora PostgreSQL | 0
0
Total Person Days [B] | 0
Delivery Oversight[C] - (10 to 15 % of A) | 0
Grand Total Person Days [A+B+C] | 0
Scope :
a. Migrate 1 Source_Database_Engine database - DB_NAME_1 with the Schema Objects(Tables, Indexes,Views etc ) and PL/SQL code to Target_Database_Engine
b. Migrate data from Source_Database_Engine to Target_Database_Engine to Non Prod Environment
c. Optimize and Tune the database to perform at par with On Premise
d. Design and Architect database infrastructure on AWS to cater for On Premise Arch requirements
e. Train and Enable Customer_Name resources on the Migration workflow, methodologies, tools, Services and best practises
Deliverables :
a. Migrated Schema Code
b. Migrated PL/PgSQL or T-SQL Code
c. RDS/Aurora PG/MySQL Cloud Formation Template
d. Cloud Formation Templates for DMS setup
e. Migration Runbook
f. Training Materials
Assumptions :
Access to AWS Infrastructure console for provisioning necessary services in Non Prod(Account) to be granted
Availability of skilled team members (application developer, PL/SQL developer, DBA) during the Testing - for clarifications
The estimates are based on SCT report generated on Date. Additional efforts needs to be factored for further DB/App changes and can be accomodated using Change Requests(CR's)
Risks :
No visibility of dependent objects in the Up/Down Stream systems
On-going development and release of new modules and enhancements will affect estimates.

## Staffing_Plan
Track | Resources | Level | Resource Name | W-1 | W-2 | W-3 | W-4 | W-5 | W-6 | W-7 | W-8 | W-9 | W-10 | W-11 | W-12 | W-13 | W-14 | W-15 | W-16 | W-17 | W-18 | W-19 | W-20 | Total Hours | Total Days
Database Migration - DB_NAME | DB Mgration Specialsit - Lead (R1) | Sr. Consultant | [21 empty] | 0 | 0
| DB Migration Specialist (R2) | Staff Consultant
| DB Migration Specialist (R3) | Staff Consultant
| DB Migration Specialist (R4) | Staff Consultant | bar: W-3 to W-18
| DB Migration Specialist (R5) | Associate Consultant | bar: W-3 to W-16
| DB Migration Specialist (R6) | Associate Consultant | bar: W-4 to W-16
Delivery Oversight | Local Project Manager (R7) | Sr. Consultant | [21 empty] | 0 | 0
[24 empty] | Total Days | 0
Team Size |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Database Migration - Activity | Effort (in days)
DB Name-1
| AWS Infra Setup & Arch Review | 0
| Schema & PL/PgSQL Conversion | 0
| Data Migration | 0
| Sanity Testing | 0
| Additional Features | 0
| AWS Support on Non Production Environment | 0
| AWS Post Production support for database Performance issues | 0
| Delivery Oversight | 0
| Total | 0

## Staffing Plan w Partners(1 yr+)
Resource | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Effort Months
OS - EM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12
OS - DB CON L6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 9.5
OS - DB CON L5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 10
GCCI - EM | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12
GCCI - DB CON L6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 11.5
GCCI - DB CON L5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11.5
GCCI - DB CON L5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 8
GCCI - DB CON L4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 9
GCCI - DB CON L4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 10
PARTNER - DB CON L6 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11
PARTNER - DB CON L5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 11
PARTNER - DB CON L5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 10
PARTNER - DB CON L5 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 8
PARTNER - DB CON L5 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 7
PARTNER - DB CON L4 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 9
PARTNER - DB CON L4 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 8
PARTNER - DB CON L4 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
PARTNER - DB CON L4 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10
PARTNER - DB CON L4 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 8
PARTNER - DB CON L4 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 8
| 4.5 | 13 | 17 | 20 | 20 | 20 | 20 | 19.5 | 19.5 | 18.5 | 13.5 | 8 | 193.5
Target | 12 months
OS -- Onsite | [9 empty] | Partner % | 51.68%
GCC1
PARTNER

## Legends
DB_Migration_Summary
Sections | Details | Source/Method to Derive Efforts
AWS Infrastrucute Provisioning & Architecture Design Review
Infra Setup & Provisioning Services used during Migration- APG, RDS ,DMS,CFT,Terraform etc | This efforts are estimated for Provisioning and Configuring the Infrastructure on AWS for the recommeded Architecture. This could be typically be using AWS Services for database RDS/Aurora with HA, Read Replicas, DR, upstream, downstream etc and the eco-system for the give database landscape. This is deployed using Cloud Formation Template or any other IAC tool | Fixed Days
Design Review - Database design, failover/HA | This efforts are estimated for Review of recommended database Architecture on AWS | Fixed Days
Schema & PL/PgSQL Code Conversion
Schema | The efforts are estimated for Schema - Tables, Constraints, Sequences, Indexes etc . The efforts are derived manually by assessing the SCT Report for the objects not converted and the review of the converted ones | Fixed Days
PL/PgSQL, T-SQL Code Conversion | The efforts estimated for Code Conversion- Business logic residing in the backend in the form of Packages, Stored Procedures, Functions etc. SCT does the conversion for both schema and code, however for objects not able to converted maual efforts are required to be re-factored compatible to target database engine in a non production environment(Dev) | Using SCT assessment report
Review the Data Types, Proc's/Func | Datatypes are reviewed for the tables in scope and the dependent objects - Stored Procs, Functions, Application SQL's based on the representative dataset from the source environment | 5% of PL/SQL Code Conversion
Sanity Testing - Without data | A preliminary round of testing is done to check the Syntax, Semantic part of the converted code without data | 7.5 % of PL/SQL Code conversion
Data Migration
Data Migration | The efforts are factored for migrating the data either using native Dump/Restore, DMS, Snowball or any replication tools. The efforts are estimated for the number of iterations on a non production environment(Dev) | Fixed Days
Sanity Testing | A secondary round of testing is done to check the Syntax, Semantic part of the converted code WITH data | 7.5 % of PL/SQL Code conversion
Embeded Application SQL's Migration | The efforts are factored for Application SQL's embeded in the application code - JAVA, .NET needs to be converted. The SQL's needs to be re-factored compatible to the target database engine | Fixed Days
AWS Support for Non Prod Environment
Propogation of migrated schema/code/Application in other environments | The efforts are factored for support extended by AWS to the customers for other environment. The converted Schema,Code is converted and handed over to the customer as deliverables to be propogated to other environments - QA, UAT, Pre-Prod & Prod. | 30% of PL/SQL Code Conversion
Full Data + CDC + Creation of Secondary objects on Staging environemt | The efforts being factored for end-to-end data migration with CDC, secondary objects in a Staging/Pre-Prod environment | Fixed Days
Failover/HA testing with application testing* - Staging, Production(until cutover) | The efforts being factored for supporting during the database failover/HA testing with application in a non-production environment | Fixed Days
Tuning , Regression & Load Testing Support Efforts - QA( 5% of PL/SQL conversion) | The efforts being factored for supporting during benchmarking of the Application/database performance is done using tools - Jmeter, Loadrunner, Manual approach | 5% of PL/SQL Code Conversion
AWS Support for Prod Environment
During Production Cutover | The efforts being factored for the support being extended by AWS Pro-Serve during the cutover, efforts depends on the downtime window typically 24-48 hrs | 1-2 Days
Post Production Support(Database Performance Issues) | The efforts being factored for the support being extended by AWS Pro-Serve to support post live for database performance issues | 15-20 Days
Efforts for Additional Features
Advanced Security, Compression & Encryption | The efforts being factored for an cloud native parity or compatible feature | Fixed Days
Password Profiles & Database Authentication using IAM/AD | The efforts being factored for an cloud native parity or compatible feature | Fixed Days
Compliance - PCI DSS requirements 3.2.1, HIPPA, GDPR | The efforts being factored for an cloud native parity or compatible feature | Fixed Days
Auditing(Need to check for exact requirements) | The efforts being factored for an cloud native parity or compatible feature | Fixed Days
Monitoring using Performance Insights, CW, Database Notifications, Enhanced Monitoring | The efforts being factored for an cloud native parity or compatible feature | Fixed Days
Training & Enablement Program by AWS
Part-1 - Primer Topics EX - Aurora PostgreSQL, DMS, CW,SNS,CFT ( Before Project KickOff) | The efforts being factored for training and enabling the customer or partner team members before the Project Kick-Off as Part-1 | 2 Days
Part-2 - Dive Deep Topics EX : Query Tuning, Database Tuning, PL/PgSQL Best Practises, Operational/Maintenance Activities on Aurora PostgreSQL | The efforts being factored for training and enabling the customer or partner team members during the mid of the Project as Part-2 | 3 Days
Delivery Oversight
Deliver Oversight | The efforts being factored for Project Management by ESM/PM for overseeing the project | 10% of overall estimates
Scope
a. Migrate 1 Source_Database_Engine database - DB_NAME_1 with the Schema Objects(Tables, Indexes,Views etc ) and PL/SQL code to Target_Database_Engine | These are the databases/schemas in scope for migration .Please change the Source_Database_Engine, DB_Name_1, Target_Database_Engine to a appropriate value | NA
b. Migrate data from Source_Database_Engine to Target_Database_Engine to Non Prod Environment | This is for Data Migration, change the Source_Database_Engine & Target_Database_Engine appropriately
Assumptions
The estimates are based on SCT report generated on Date. Additional efforts needs to be factored for further DB/App changes and can be accomodated using Change Requests(CR's) | The estimates are based on the SCT reports generated on a certain Date, change the date and call out additional | NA
Risks
No visibility of dependent objects in the Up/Down Stream systems | Any unknown risks, which you don't have the visibility needs to be called out
Staffing_Plan | This sheet is about the resource planning as per the various stages/activities involved during the migration within the given alloted/estimated hours | NA
RACI_Matrix | This sheet is about the Roles/Responsibilities for each teams involved - AWS/Customer/Partner | NA
Sample_SCT_Report | This is an extract from Schema Conversion Tool Report- CSV format with Action codes/occurences. You may assign weighted hours to each of them to arrive at a ball park number for both schema or code conversion | NA

## RACI_Matrix
| AWS | Patner/Customer Name | Notes | Responsible (R): Will perform the activities Accountable (A): Delegates the work and will review for completion Consulted (C): Provides inputs and support the activity Inform (I): Informed on the activity
Project Management
Manage overall migration scope | C,I | R,A
Manage Database Migration team | R,A | C,I
Pre-Work
Assessment of DB code migration for modules Module-1, Module-2 & Module-3 | R | A,C,I
Database Code Migration
Schema and Database Code migration | R | A,C,I
Sanity Testing | R,A | C,I
Data Migration | R | A,C,I
Build environment migration | C,I | R,A
Changes to DB migration under CR (schemas, tables, data, packages, stored procedures, functions etc. used by the application) | I | R,A,C
Functional Testing | C,I | R,A
Non Production environment Support
Deployment of CFT's, Schema & Database code | C,I | R,A
Application Runtime Support
Support for runtime issues arising out of application migration to Database | R | A,C,I
Perform Application Level Unit Testing | C,I | R,A
Perform Acceptance, Load and Regression Tests | C,I | R,A
Replicate Migrated Environments | I | R,A,C
End User Acceptance and Management | I | R,A,C

## Sample_SCT_Report_DB_Name-1
Source database:
Category | Number of objects | Objects automatically converted | Objects with simple actions | Objects with medium-complexity actions | Objects with complex actions | Total lines of code
PACKAGE_COLL_TYPE | 6 | 5 | 1 | 0 | 0
PACKAGE_CONSTANT | 32 | 32 | 0 | 0 | 0
PACKAGE_CURSOR | 1 | 0 | 0 | 0 | 1
PACKAGE_EXCEPTION | 1 | 1 | 0 | 0 | 0
PACKAGE_VARIABLE | 23 | 23 | 0 | 0 | 0
SEQUENCE | 3 | 3 | 0 | 0 | 0 | 21
PACKAGE_PROCEDURE | 24 | 0 | 0 | 0 | 24
PACKAGE_FUNCTION | 66 | 3 | 0 | 0 | 63
PACKAGE_TYPE | 1 | 1 | 0 | 0 | 0
PACKAGE | 9 | 9 | 0 | 0 | 0 | 6383
FUNCTION | 2 | 1 | 0 | 0 | 1 | 13
PROCEDURE | 5 | 0 | 0 | 0 | 5 | 386
VIEW | 7 | 4 | 2 | 1 | 0 | 109
INDEX | 22 | 18 | 0 | 0 | 4 | 264
CONSTRAINT | 18 | 18 | 0 | 0 | 0
TABLE | 55 | 52 | 3 | 0 | 0 | 1752
SCHEMA | 1 | 1 | 0 | 0 | 0 | 1
SQL_syntax_elements_number | 30350
CATEGORY | object_name | EXCEPTION | actionitem | occurence | complex | medium | simple
VIEW |  | Unable to resolve objects | 5293 | 9 | 0 | 0 | 9
VIEW |  | PostgreSQL doesn't support the view with invalid status | 5320 | 1 | 0 | 0 | 1
PACKAGE FUNCTION |  | Unable to convert unsupported datatypes | 5028 | 79 | 79 | 0 | 0
PACKAGE FUNCTION |  | Unable to convert functions | 5340 | 7 | 7 | 0 | 0
PACKAGE FUNCTION |  | Unable to convert unsupported datatypes | 5028 | 9 | 9 | 0 | 0
PACKAGE FUNCTION |  | Unable to convert functions | 5340 | 5 | 5 | 0 | 0
PROCEDURE |  | Unable to convert functions | 5340 | 5 | 5 | 0 | 0
PROCEDURE |  | Unable to convert simple usage of unsupported datatype objects | 5029 | 3 | 3 | 0 | 0
PROCEDURE |  | Unable to convert functions | 5340 | 2 | 2 | 0 | 0
PROCEDURE |  | Unable to convert statements with dynamic SQL statement | 5334 | 1 | 0 | 0 | 1
PACKAGE FUNCTION |  | Unable to convert unsupported datatypes | 5028 | 24 | 24 | 0 | 0
PACKAGE FUNCTION |  | Unable to convert functions | 5340 | 4 | 4 | 0 | 0
PACKAGE PROCEDURE |  | Converted code might be incorrect because of the dynamic SQL | 5628 | 1 | 0 | 0 | 1
PACKAGE PROCEDURE |  | Unable to convert functions | 5340 | 41 | 41 | 0 | 0
PACKAGE PROCEDURE |  | Unable to convert complex usage of unsupported datatype objects | 5030 | 1 | 1 | 0 | 0
TABLE |  | PostgreSQL doesn't support index-organized table | 5581 | 1 | 0 | 0 | 1
TABLE |  | Table contains LOB column(s) | 5659 | 1 | 0 | 0 | 1
TABLE |  | Table contains LOB column(s) | 5659 | 1 | 0 | 0 | 1
VIEW |  | Converted functions depends on the time zone settings | 5584 | 1 | 0 | 0 | 1
VIEW |  | PostgreSQL doesn't support the view with invalid status | 5320 | 1 | 0 | 0 | 1
INDEX |  | Unable to convert functions | 5340 | 1 | 1 | 0 | 0
INDEX |  | Unable to convert functions | 5340 | 1 | 1 | 0 | 0
INDEX |  | Unable to convert functions | 5340 | 1 | 1 | 0 | 0
INDEX |  | Unable to convert functions | 5340 | 1 | 1 | 0 | 0
FUNCTION |  | Unable to convert functions | 5340 | 2 | 2 | 0 | 0
FUNCTION |  | Unable to convert unsupported datatypes | 5028 | 3 | 3 | 0 | 0
PROCEDURE |  | Unable to convert functions | 5340 | 2 | 2 | 0 | 0
PROCEDURE |  | Unable to convert unsupported datatypes | 5028 | 9 | 9 | 0 | 0
PACKAGE COLLECTION TYPE |  | PostgreSQL doesn't support TYPE ... IS REF CURSOR declaration | 5225 | 1 | 0 | 0 | 1
PACKAGE CURSOR |  | Unable to convert functions | 5340 | 1 | 1 | 0 | 0
PACKAGE CURSOR |  | Unable to automatically transform the SELECT statement | 5578 | 1 | 1 | 0 | 0